## Overview
Project Name | Report Owner | Reporting Period | Overall Completion % | Executive Highlights | SharePoint / Source Link | Last Updated
Securitization Modernization 2025 |  | Q4 2025 | 71% | Development of the Enricher capability completed; RI capability on track for December completion. | https://freddiemac.sharepoint.com/...link...

## Milestones & Capabilities
Domain | Milestone # | Capability (BPR Milestone) | Tier / Reporting Stream | Baseline Start | Baseline End | Target Start | Target End | Status | Budget / CR Tag | Comments
Onboarding | 1 | Initiate Security Req - Pseudo Pool & XSIO Strip MVP1 | App Mod | Jan-25 | Mar-25 | Jan-25 | Mar-25 | Completed
Collateral Mgmt | 4 | Collateral Management - Pseudo Pool and XSIO Strip MVP1 | ARM+ to CSS | Mar-25 | May-25 | Mar-25 | May-25 | Completed
Onboarding | 8 | Mods and Reinstates Feature Ready | MF Retirement | Sep-25 | Oct-25 | Sep-25 | Oct-25 | In Progress | CR Issued

## Risks & Mitigations
Risk ID | Description | Severity | Owner | Due Date | Status | Mitigation Strategy
R-001 | Dependency delay on CSS integration | High | PMO Lead | 10/30/2025 | Open | Weekly standups with CSS team to unblock items

## Upcoming Deliverables
Deliverable | Owner | ETA | Readiness | Notes
EBM Enhanced Publications | Tech Lead | Dec 2025 | In Progress | Final testing phase in Q4

## Executive Summary
Freddie Mac Securitization Modernization – Executive Summary
Highlights:
- Enricher capability complete; RI capability on track for Dec completion.
- CSS testing initiated for ARM+ products.
- Current roadmap completion at 71% (as of Oct 2025).